## Hoja1
Gantt Chart
Task | Start date | Duration (days) | End date | Completion | Task | date | days | days completed | Start plan date | days
Literature Review and Preliminary Analysis | 2024-02-29 | 14 | 2024-03-14 | 100% | Literature Review and Preliminary Analysis | 2024-02-29 | 14 | 14 | 2024-02-29 | 14
PAC01 - Definition and Work Plan | 2024-03-12 | 0 | 2024-03-12 |  | PAC01 - Definition and Work Plan | 2024-03-12 | 1 | 1 | 2024-03-12 | 1
Workflow Optimization | 2024-03-15 | 21 | 2024-04-05 | 100% | Workflow Optimization | 2024-03-15 | 21 | 21 | 2024-03-15 | 21
Quality Control | 2024-03-22 | 21 | 2024-04-12 | 100% | Quality Control | 2024-03-22 | 21 | 21 | 2024-03-22 | 21
PAC02 - Development of the work Phase 1 | 2024-04-09 | 1 | 2024-04-09 |  | PAC02 - Development of the work Phase 1 | 2024-04-09 | 1 | 1 | 2024-04-09 | 1
Cluster markers analysis | 2024-04-01 | 35 | 2024-05-13 | 80% | Cluster markers analysis and Phenotypic Characterization | 2024-04-01 | 35 | 28 | 2024-04-01 | 42
CCC Analysis | 2024-04-22 | 14 | 2024-05-06 |  | CCC Analysis | 2024-04-22 | 14 | 14 | 2024-05-06
Biological description | 2024-05-06 | 14 | 2024-05-20 |  | Biological description | 2024-05-06 | 14 | 0 | 2024-05-06 | 14
PEC03 - Development of the work Phase 2 | 2024-05-14 | 1 | 2024-05-14 |  | PEC03 - Development of the work Phase 2 | 2024-05-14 | 1 | 1 | 2024-05-15 | 1
Preparation of the Manuscript | 2024-05-14 | 32 | 2024-06-15 |  | Preparation of the Manuscript | 2024-05-14 | 32 | 0 | 2024-05-14 | 32
PEC04 - End of the Project | 2024-06-18 | 1 | 2024-06-18 |  | PEC04 - End of the Project | 2024-06-18 | 1 | 1 | 2024-06-18 | 1
Gantt Diagram of the followed timeline during the project.
Formulas:
End date = [Start date]+14
End date = [Start date]+[Duration (days)]
date = [Start date]
Start plan date = [date]
Start plan date = [End date]
Start date = [Start date, row above]+7
Start date = [Start date, row above]+7*3